## Feature List
# | Feature | Category | Full Explanation | Backend Components (Java/Spring) | Key API Endpoint(s) | Priority | Phase | Status
1 | User Registration & Login | Authentication | Lets a person create an account with email/phone and password, and log back in. Passwords are hashed (BCrypt) before storage; on successful login the server issues a signed token the client uses for every future request. | AuthController, UserService, User entity, BCryptPasswordEncoder | POST /auth/register, POST /auth/login | Must-have | 1 | Not started
2 | JWT-Based Authentication | Authentication | Instead of sessions, the backend issues a stateless JSON Web Token on login. Every protected endpoint reads the token from the Authorization header, validates its signature/expiry, and resolves the current user — no server-side session storage needed, which scales better. | JwtUtil, JwtAuthFilter, SecurityConfig (Spring Security) | Filter on all /api/** routes | Must-have | 1 | Not started
3 | Role-Based Access Control | Authentication | Distinguishes normal users from admins/station operators. Admin-only endpoints (adding a station, editing charger status) are guarded so a regular user's token can never reach them, even if they know the URL. | Role enum, @PreAuthorize annotations, SecurityConfig | Guards on /admin/** routes | Must-have | 1 | Not started
4 | Vehicle Profile Management | User & Vehicle | A user can add one or more EVs to their account (model, battery capacity in kWh, max charging speed, connector type). This data feeds every later calculation — compatible chargers, charging time, and cost estimates all depend on it. | VehicleController, VehicleService, Vehicle entity (linked to User) | POST /users/{id}/vehicles, GET /users/{id}/vehicles | Must-have | 1 | Not started
5 | Charging Station CRUD | Station Management | Core admin capability to add, update, and remove charging stations — name, address, latitude/longitude, operating hours, and the list of chargers it hosts. This is the data every other feature (map, search, sessions) is built on top of. | StationController, StationService, Station entity | POST/GET/PUT/DELETE /stations | Must-have | 1 | Not started
6 | Charger/Connector Management | Station Management | Each station can have multiple physical chargers, each with its own type (AC, DC, Fast/CCS2/Type-2), max power output in kW, and price per kWh. Managing them separately from the station lets one location report different chargers as busy vs free independently. | ChargerController, ChargerService, Charger entity (linked to Station) | POST/GET/PUT /stations/{id}/chargers | Must-have | 2 | Not started
7 | Real-Time Charger Status | Station Management | Every charger has a live status — Available, Occupied, or Offline (out of service) — that updates the instant a session starts, ends, or a fault is reported. The map and search results always reflect current reality instead of stale data. | ChargerStatusService, status field on Charger, event listeners | GET /chargers/{id}/status, PATCH /chargers/{id}/status | Must-have | 2 | Not started
8 | Geolocation-Based Nearby Search | Search & Discovery | Given the user's current latitude/longitude, returns stations within a radius, sorted by distance. Uses the Haversine formula (or a spatial DB extension) to compute distance server-side rather than pulling every station to the client. | StationSearchService, Haversine utility, MySQL spatial index or PostGIS | GET /stations/nearby?lat=&lng=&radiusKm= | Must-have | 2 | Not started
9 | Advanced Station Filtering | Search & Discovery | Lets a user narrow results by charger type, minimum charging speed, maximum price per kWh, and current availability in one query — e.g. 'fast DC chargers under Rs.10/kWh within 10 km that are free right now.' | StationSearchService with dynamic JPA Specifications/Criteria API | GET /stations/search?type=&maxPrice=&available=true | Should-have | 2 | Not started
10 | Station Detail View | Search & Discovery | Returns everything about one station in a single call: address, all its chargers with live status and pricing, average rating, amenities, and recent reviews — everything the 'station details' screen needs in one round trip. | StationController, DTO aggregating Station + Chargers + Reviews | GET /stations/{id} | Must-have | 2 | Not started
11 | Favorite Stations | User Engagement | A user can bookmark stations they use often for one-tap access later, instead of searching every time. Simple many-to-many relationship between users and stations. | FavoriteController, Favorite join entity | POST /users/{id}/favorites/{stationId}, GET /users/{id}/favorites | Should-have | 2 | Not started
12 | Start / Stop Charging Session | Charging Engine | The core transactional feature: a user selects a charger and starts a session, which locks that charger as Occupied and records start time, starting battery %, and the vehicle used. Stopping the session releases the charger and finalizes the record. | ChargingSessionController, ChargingSessionService, ChargingSession entity | POST /charging/start, POST /charging/{id}/stop | Must-have | 3 | Not started
13 | Charging Simulation Engine | Charging Engine | Since real hardware isn't wired up yet, this scheduled service simulates battery % rising over time based on charger power (kW) and vehicle battery capacity (kWh), so 'time remaining' and 'current battery %' feel real and can later be swapped for actual telemetry. | @Scheduled task in ChargingSimulationService; energy = power x time, %=energy/capacity | Internal service, exposed via GET /charging/{id}/status | Must-have | 3 | Not started
14 | Live Charging Progress via WebSocket | Real-Time | Pushes battery %, kW draw, and time-remaining updates to the user's dashboard every few seconds without the client polling. Uses STOMP over WebSocket so the progress bar animates in near real time. | WebSocketConfig, ChargingProgressController (@MessageMapping), STOMP broker | WS /topic/charging/{sessionId} | Should-have | 4 | Not started
15 | Cost Estimator | Business Logic | Before or during a session, calculates energy required (target% - current%) x battery capacity, then multiplies by the charger's price/kWh to estimate cost and, using charger power, estimated time to reach the target. | CostEstimatorService (pure calculation service, no persistence needed) | GET /charging/estimate?currentPct=&targetPct=&vehicleId=&chargerId= | Must-have | 3 | Not started
16 | Dynamic Pricing | Business Logic | Price per kWh can vary by station, charger type, and even time of day (peak vs off-peak), rather than a single fixed number. Adds realism and gives the recommendation engine a real variable to optimize on. | PricingService, PricingRule entity (station/time-based rules) | GET /chargers/{id}/price?time= | Nice-to-have | 5 | Not started
17 | Charging History | Analytics | Every completed session (date, station, energy delivered, cost, duration) is stored permanently and can be listed per user, most-recent first, forming the record behind receipts and analytics. | ChargingSessionRepository query methods, pagination via Pageable | GET /users/{id}/charging/history | Must-have | 3 | Not started
18 | Usage Analytics Dashboard | Analytics | Aggregates a user's history into monthly totals — spend, energy consumed, number of sessions, average session duration — computed with SQL aggregate functions so the frontend can render trend charts. | AnalyticsService using JPA @Query with SUM/AVG/GROUP BY month | GET /users/{id}/analytics/monthly | Should-have | 5 | Not started
19 | Trending Stations Algorithm | Recommendation | Ranks stations by a computed 'trending score' combining recent session count, average rating, and current busy percentage, refreshed on a schedule so 'popular near you' reflects real recent demand, not just raw popularity. | TrendingScoreService (@Scheduled recompute), weighted formula | GET /stations/trending | Should-have | 5 | Not started
20 | 'Best Charger For Me' Recommendation Engine | Recommendation | The signature feature: scores every nearby, compatible charger on distance, current availability, charging speed, price, station rating, and queue length, combines them into a single weighted score, and returns the top pick with a plain-language reason. | RecommendationService, weighted-scoring algorithm, RecommendationDTO | GET /recommendations/best-charger?userId=&lat=&lng= | Should-have | 5 | Not started
21 | Ratings & Reviews | User Engagement | Lets users rate a station (1-5 stars) and leave a short comment after a session, feeding both the station detail page and the trending-score calculation. | ReviewController, ReviewService, Review entity linked to Station and User | POST /stations/{id}/reviews, GET /stations/{id}/reviews | Should-have | 4 | Not started
22 | Push/Email Notifications | Notifications | Fires events at key moments — battery reaching 80%, session complete, favorite station now cheaper, charger going offline — and delivers them via email (or push, if a mobile client is added later) using an async, event-driven design so the charging flow itself never blocks on sending a message. | NotificationService, Spring Events (@EventListener, @Async), JavaMailSender | Internal event-driven, GET /users/{id}/notifications | Should-have | 4 | Not started
23 | Payment Integration | Payments | Charges the user for a completed session, either via a mock in-house wallet (simplest for a resume project) or a real gateway (Razorpay/Stripe test mode). Session cost from the charging engine becomes the payment amount. | PaymentController, PaymentService, Payment entity, gateway SDK integration | POST /payments/charge, GET /payments/{id} | Should-have | 5 | Not started
24 | Invoice / Receipt Generation | Payments | Produces a downloadable PDF or structured JSON receipt for each completed, paid session — station, energy delivered, duration, and cost — using the same data already captured by the charging and payment services. | InvoiceService, PDF generation (e.g. OpenPDF), reuses ChargingSession + Payment data | GET /charging/{id}/invoice | Nice-to-have | 6 | Not started
25 | Booking / Reservation System | Advanced | Lets a user reserve a specific charger for a future time slot rather than only starting a session on arrival, preventing wasted trips to a busy station. Requires a slot-conflict check so two users can't book the same charger simultaneously. | BookingController, BookingService, Booking entity with time-range overlap validation | POST /bookings, GET /stations/{id}/bookings | Nice-to-have | 6 | Not started
26 | Queue / Waitlist for Busy Stations | Advanced | When every charger at a popular station is occupied, a user can join a first-come-first-served waitlist and gets notified automatically when one frees up, instead of repeatedly refreshing the app. | QueueService, Queue entity, triggered by the same event that frees a Charger | POST /stations/{id}/queue, DELETE /stations/{id}/queue/{userId} | Nice-to-have | 6 | Not started
27 | Multi-Vehicle Support | User & Vehicle | A user with more than one EV can switch which vehicle a session is tied to, and history/analytics can be filtered per vehicle — useful for households or small fleets. | Extends Vehicle entity (already one-to-many with User); filter param on history endpoints | GET /users/{id}/charging/history?vehicleId= | Nice-to-have | 3 | Not started
28 | Charger Fault Reporting | Station Management | A user or automated health-check can flag a charger as faulty, which flips it to Offline, removes it from search/recommendation results immediately, and creates a maintenance ticket for the operator. | FaultReportController, FaultReport entity, listener that updates Charger.status | POST /chargers/{id}/report-fault | Nice-to-have | 6 | Not started
29 | Admin Operations Dashboard (API) | Admin | A set of endpoints purpose-built for an admin frontend: station/charger management, viewing all active sessions system-wide, resolving fault reports, and pulling platform-wide usage stats. | AdminController (secured by role), aggregation queries across all core entities | GET /admin/sessions/active, GET /admin/stats | Should-have | 6 | Not started
30 | Global Exception Handling | Backend Architecture | One centralized handler converts every exception (not-found, validation failure, insufficient battery, unauthorized) into a consistent JSON error shape with the right HTTP status, so the frontend never has to guess the error format. | @ControllerAdvice class, custom exception classes (ResourceNotFoundException, etc.) | Applies to all endpoints | Must-have | 1 | Not started
31 | Input Validation | Backend Architecture | Validates every incoming request body (registration fields, vehicle data, session parameters) before it touches business logic, rejecting malformed input early with clear field-level error messages. | jakarta.validation annotations (@NotNull, @Email, @Min) on DTOs | Applies to all POST/PUT endpoints | Must-have | 1 | Not started
32 | Rate Limiting & API Security | Security | Throttles repeated requests per user/IP (especially on login and session-start) to blunt brute-force and abuse, layered on top of the JWT authentication already in place. | Bucket4j filter or Spring Cloud Gateway rate limiter, SecurityConfig | Filter on /auth/** and /charging/start | Nice-to-have | 6 | Not started
33 | Caching Layer | Performance | Caches read-heavy, slow-changing data — nearby-station search results, station details — for a short TTL so repeated map refreshes don't hit the database every time. | Spring Cache abstraction (@Cacheable) backed by Redis | Wraps StationSearchService methods | Nice-to-have | 6 | Not started
34 | API Documentation | DevOps | Auto-generates interactive API docs from the controller annotations, so every endpoint (request/response shape, auth requirement) is browsable and testable without a separate Postman collection. | springdoc-openapi (Swagger UI) | GET /swagger-ui.html | Should-have | 7 | Not started
35 | Automated Testing | Quality | Unit tests for service-layer logic (cost calculation, recommendation scoring) and integration tests for controllers (auth flow, session start/stop) catch regressions before a demo. | JUnit 5, Mockito, @SpringBootTest, @WebMvcTest | N/A (test suite, not an endpoint) | Should-have | 7 | Not started
36 | Logging & Monitoring | DevOps | Structured logs on every request/error plus a health-check endpoint let you see the app is alive and diagnose issues without attaching a debugger. | SLF4J + Logback, Spring Boot Actuator | GET /actuator/health | Nice-to-have | 7 | Not started
37 | Containerized Deployment | DevOps | Packages the Spring Boot app and MySQL into Docker containers with a docker-compose file, so the whole backend spins up with one command on any machine. | Dockerfile, docker-compose.yml, application-docker.properties | N/A (deployment artifact) | Nice-to-have | 7 | Not started

## Roadmap
Phase | Goal | Steps | Deliverable / Definition of Done | Est. Duration
Phase 1 - Foundations | Project skeleton, database, auth | 1. Create Spring Boot project (Web, JPA, Security, MySQL Driver, Validation) via Spring Initializr. 2. Design the core schema: User, Vehicle, Station, Charger, ChargingSession, Payment, Review, Favorite. 3. Implement User entity + registration/login with BCrypt password hashing. 4. Add JWT generation/validation (JwtUtil) and a security filter chain (SecurityConfig). 5. Add roles (USER/ADMIN) and @PreAuthorize guards. 6. Add Vehicle CRUD tied to the logged-in user. 7. Add global exception handling (@ControllerAdvice) and request validation. | Can register, log in, receive a JWT, and call a protected endpoint with it. Vehicle CRUD works end to end. | 1-2 weeks
Phase 2 - Stations & Search | Station/charger data + discovery | 1. Build Station and Charger entities and admin CRUD endpoints. 2. Add charger status field (Available/Occupied/Offline) with an update endpoint. 3. Implement Haversine-based 'nearby stations' query. 4. Add filtering (type, price, availability) using JPA Specifications. 5. Add station detail endpoint aggregating chargers + reviews. 6. Add Favorites (many-to-many User<->Station). | Given lat/lng, the API returns real nearby stations with live charger status, filterable and sortable by distance. | 1-2 weeks
Phase 3 - Charging Engine | The core simulated charging flow | 1. Build ChargingSession entity + start/stop endpoints; starting locks the charger as Occupied. 2. Build the simulation service: a scheduled job that advances battery % based on charger power and vehicle capacity. 3. Build the Cost Estimator service (energy needed x price/kWh) as a standalone, reusable calculation. 4. Persist finished sessions into charging history with final energy/cost/duration. 5. Write unit tests for the simulation and cost math specifically. | Starting a session shows battery % climbing over time and a correct final cost/energy figure when stopped. | 2 weeks
Phase 4 - Real-time & Engagement | Live updates, reviews, notifications | 1. Add WebSocket/STOMP config and push charging-progress updates on a timer. 2. Add Review entity + endpoints for rating a station after a session. 3. Add an event-driven Notification service (Spring @EventListener + @Async) for milestones like '80% charged'. 4. Wire notification triggers into the simulation service's existing events. | Dashboard updates without polling; users can review stations; key events generate a notification record. | 1-2 weeks
Phase 5 - Analytics & Recommendations | Turn stored data into insight | 1. Build monthly analytics aggregation (spend, energy, session count) with SQL GROUP BY queries. 2. Build the Trending Stations score (recent usage + rating + busy%), recomputed on a schedule. 3. Build the 'Best Charger For Me' recommendation service: score by distance, speed, price, rating, queue length. 4. Add dynamic pricing rules if time allows (station/time-based price variation). | A user can hit one endpoint and get a ranked, explained recommendation; analytics endpoints return correct monthly rollups. | 1-2 weeks
Phase 6 - Payments & Admin | Money and operator-side tooling | 1. Integrate a payment flow (mock wallet, or Razorpay/Stripe test mode) tied to session cost. 2. Generate a receipt/invoice per paid session. 3. Add booking/reservation and queue/waitlist features if time allows. 4. Build admin endpoints: active sessions, fault reports, platform-wide stats. 5. Add rate limiting on sensitive endpoints (login, session-start) and a Redis cache for hot read paths. | A session can be paid and produces a receipt; an admin can see system-wide activity through dedicated endpoints. | 2 weeks
Phase 7 - Hardening & Delivery | Make it demo- and interview-ready | 1. Add Swagger/OpenAPI docs for every controller. 2. Write unit tests (JUnit/Mockito) for service logic and integration tests for key controllers. 3. Add structured logging and Spring Boot Actuator health checks. 4. Containerize with Docker + docker-compose (app + MySQL). 5. Write the README: architecture diagram, setup steps, sample requests. | Anyone can clone the repo, run 'docker-compose up', open Swagger UI, and exercise the whole API. | 1 week